# Visual Clothing Search Project Brief

Two-week work plan  |  September 30–October 13, 2026

# Project goal

Build a website that accepts a photo of a garment and suggests up to five similar products with prices and store links. The two-week goal is a usable, demonstrable prototype. Start with women’s tops and a defined catalog; confirm the category and data source at the beginning of the project.

# User journey

The user uploads a clear photo of one garment, optionally enters its original price and a maximum budget, and starts the search. The website compares the photo with catalog images, applies the selected filters, and returns results. Each card shows an image, product name, store, price, currency, purchase link, and price-check date. If no suitable match is found, display a clear message.

# Search definitions

Similar means the same garment category with a close cut and visible details, such as sleeve length, neckline, and pattern. Color influences ranking unless the user requests another color. Use an existing model to represent images numerically and review results manually; its similarity score is not a verified match percentage.

Cheaper means a product price below the original price entered by the user, in the same currency. Initially, compare item prices only, excluding shipping and taxes, and state this beside the savings. Without an original price, return results within the budget. Rank by similarity first and allow suitable results to be sorted by price.

Good initially means a useful visual match, valid product information, and a working store link. A photo cannot establish fabric quality, fit, or store reliability.

# Scope and success target

Prepare approximately 2,000–5,000 products if a suitable source offers images, prices, links, and permitted use. Include a color filter, including black. Free-text requests such as “the same top, but in black” are an extension after basic search works. Proposed evaluation target: for 15 of 20 query photos from outside the catalog, at least one of the top five results meets the similarity definition. All results must satisfy the selected filters.

# Two-week Gantt chart

Day 1 is September 30. The plan assumes about four hours per day; a suitable data source is a prerequisite for further development.

| Task | 1–2 | 3–4 | 5–6 | 7–9 | 10–11 | 12–14 |
| --- | --- | --- | --- | --- | --- | --- |
| Define scope and validate catalog | ● |  |  |  |  |  |
| Prepare data and image search |  | ● |  |  |  |  |
| Rank and filter price and color |  |  | ● |  |  |  |
| Build interface and connect search |  |  |  | ● |  |  |
| Show savings and handle errors |  |  |  |  | ● |  |
| Test, fix, and deploy |  |  |  |  |  | ● |